## Master Launch Schedule
Exos Aerospace Master Launch Schedule | [5 empty] | Today's Date--> | 2020-05-26
Scheduled Launch Date: |  |  | 2020-08-15 11:00 | Scheduled Launch Time: | 44058.4583 | Days to launch--> | 81.4583
Pre-Launch and Regulatory Milestones
Item # | # of days before Launch | Action Date | Description | Point of Contact | Phone Number | Email Address | Notes:
1 | 67 | 2020-06-09 11:00 | Initial Hold Down Testing | Internal
2 | 65 | 2020-06-11 11:00 | Spaceport Scheduling | Bill Gutman | 575-520-5433 | bill.gutman@spaceportamerica.com
3 | 60 | 2020-06-16 11:00 | Send 60 Day Notification Including Payload Manifest. (Click for Contact List) | Sherman Council/Henry Lampazzi | 202-570-5819 | sherman.council@faa.gov; Henry.Lampazzi@faa.gov; AST-400@faa.gov; annette.parks@faa.gov | Notification by Email | 60 Day Launch Notification, Click for requirements.
4 | 45 | 2020-07-01 11:00 | Request Launch Insurance Coverage, Send Certificates to AST when complete. | Dana or Jason at Gallegher | Dana Cell: 713-828-7319 | dana.smith@ajg.com; Jason.Hendrix@ajg.com | Request by Email, Follow up by Phone
5 | 45 | 2020-07-01 11:00 | Place Reservation for Crew Van with Enterprise Van Rental Specialties | Sean Spradling | 972-519-9697 | sean.j.spradling@erac.com | Request Chevy Express 15 Passenger Van by Phone, Follow up by Email. Do Not Rent the Ford Transit!
6 | 45 | 2020-07-01 11:00 | Place Reservation for Hotel in Las Cruces | Fairfield Inn by Marriott |  | (Needs Contact Info)
7 | 30 | 2020-07-16 11:00 | Send Insurance Certificates to AST | AST-400, Sherman Council |  | AST-400@faa.gov
8 | 30 | 2020-07-16 11:00 | Request Travel Insurance | Roanoak Trade, Tom Moran | 847-969-8232 | Tom.Moran@roanokegroup.com | Request by Email, Follow up by Phone
9 | 30 | 2020-07-16 11:00 | File Cross Waivers with AST, Send Final Payload Manifest. | Ken Wong, AST-200 | (202) 267-8465 | Ken.Wong@faa.gov; henry.lampazzi@faa.gov; sherman.council@faa.gov; AST-400@faa.gov; | Notify by email, Send original signature copies by US Mail
10 | 21 | 2020-07-25 11:00 | Complete System Integration test | Internal
11 | 15 | 2020-07-31 11:00 | 15 Day Notification, Make the 10 Day Notification at the same time and include all of the required information. | Sherman Council/Henry Lampazzi | 202-570-5819 | sherman.council@faa.gov; Henry.Lampazzi@faa.gov; AST-400@faa.gov; annette.parks@faa.gov | Notification by Email | 15 Day Noification to AST, Click for Requirements.
12 | 10 | 2020-08-05 11:00 | 10 Day notice to ARTCC and ZAB | Tim McHale/ZAB 530 |  | 9-asw-zab530@faa.gov; 9-AWA-AJR-SPCE.OPS@faa.gov; spaceops@spaceportamerica.com; Melanie.Ramos@faa.gov; beth.e.adams@faa.gov | Notification done by Email at the 15 day mark | 10 Day Notification to ZAB, Click for requirements.
13 | 5 | 2020-08-10 11:00 | Crane Truck Depart for Spaceport | Jessica Harrell/Brian Mott | 214-557-5536 | Also Verify Van rental pickup | The van should be brought to the shop and prepared for travel.
14 | 3 | 2020-08-12 11:00 | Crew depart for Spaceport | Internal
15 | 2 | 2020-08-13 11:00 | 1st day of Setup | Internal
16 | 2 | 2020-08-13 11:00 | Payload Integration Begins | Brad Clouser |  | Brad to oversee Payload readiness and integration timing | To Be Done at the Spaceport Provided Facility.
17 | 2 | 2020-08-13 11:00 | Vehile Dry Run approximately 1:00 PM
18 | 1 | 2020-08-14 11:00 | 2nd Day of Setup | Internal
19 | 1 | 2020-08-14 11:00 | Mission Readiness Review | All Attendees
20 | 0 | 2020-08-15 11:00 | Launch Day | Everyone
21 | 0 | 2020-08-15 11:00 | Post Flight Briefing
Note on G13: Phil Exos: Address to send Cross Waivers: FAA/AST 200 Licensing Division ATTN: Kenneth Wong 800 Independence Ave SW FOB10A, Room 331 Washington, DC 20591 PH:(202) 267-8465 Email List: Ken.Wong@faa.gov; henry.lampazzi@faa.gov; sherman.council@faa.gov; AST-400@faa.gov;
Note on H13: Phil Exos: FAA/AST 200 Licensing Division ATTN: Kenneth Wong 800 Independence Ave SW FOB10A, Room 331 Washington, DC 20591 PH:(202) 267-8465

## Day 1 Setup
Day 1 Launch Setup | [5 empty] | Return to Master
Item # | Time to Launch | Action Time | Description | Participants | Estimated Time | Notes:
1 | T - 2 days | 7:00 | Depart from the Hotel | All Crew
2 |  |  | Unpack Trailer and Truck | All Crew
3 |  |  | Prep Rocket for Combined Systems Test | All Crew
4 |  | 10:00 | Combined Systems Test | 3 or 4 people
5 |  | 10:30 | Full Dry Run | All Crew
6 |  |  | Launch Pad Setup | Joseph and 2 helpers
7 |  | 1200.5 | Break For Lunch | All Crew
8 |  |  | Set Up Helium 6 Packs for Pressuization | Joseph and 1 helper
9 |  |  | Set up Recovery system | Phil and Lee
10 |  |  | Set Up Exos Wifi | Russ
11 |  |  | Set Up Truck for Pad ops (Start) | Joseph and 1 helper
12 |  | 16:00 | Get Everything back into the trailer. | All Crew
13 |  | 17:00 | Depart Launch Site | All Crew
14
15
16
17
18
19

## Day 2 Setup
Day 2 Launch Setup | [5 empty] | Return to Master
Item # | Time to Launch | Action Time | Description | Participants | Estimated Time | Notes:
1 | T - 1 days | 7:00 | Depart from the Hotel | All Crew | 75 minutes
2 |  | 8:15 | Unpack Trailer | All Crew | 30 minutes
3 |  |  | Tightness Check and Reassembly | 3 people | 2 to 3 hours
4 |  |  | Start Pressurization on Press Section | Joseph | All Day
5 |  |  | Finish Pad Ops Prep on Crane Truck | Joseph | 2 hours concurrent to Pressurization.
|  | 10:00 | Walk Through with John and Guests | John Quinn | 1 hour+ | John will escort visitors around the Launch Control Area and discuss the stations they see as well as the rocket in process.
6 |  | 12:00 | Lunch Break | All Crew
7 |  | 13:00 | Role Assignment and Training | Tiffany Long and Teresa Quinn | 1 to 2 hours | All Contractors filling Roles MUST be onsite no later than 1:00PM!
8 |  |  | LOX Transfill | 1 or 2 people
9 |  |  | Final Assembly of the Recovery system | 2 people | 2 hours
10 |  |  | Finalize Checklist and Print | Russ | 2 hours
11 |  |  | Collect and File Subassembly Checklists | Haley or Russ or Logistics Coordinator | 30 minutes | Ne a list of Subassembly Checklists. Must be filed in Vehicle Log Folder.
12 |  | 16:00 | Repack for the night, Fuel Generators and Gator | 2 People | 30 to 60 minutes
13 |  | 17:00 | Attend MRR | All Crew and Day Of Launch Attendees | 1 hour
14 |  |  | Depart Spaceport
15
16
17
18
19

## Launch Day
Launch Day | [5 empty] | Return to Master
Item # | Time to Launch | Action Time | Description | Participants | Estimated Time | Notes:
1 | 44058.25 | 5:00 | Depart from the Hotel | All Crew
2 | 44058.2083 | 6:00 | Unpack Trailer | All Crew
3 | 44058.1667 | 7:00 | Check Press Section, bump press if needed. | Joseph and Helper
4 | 44058.125 | 8:00 | Start Rocket Assembly | All Crew |  | Payload must be complete with Can going on at this time!
5 | 44058.1042 | 8:30 | Final Installation of Payload Section | All Crew | 15 minutes
6 | 44058.0938 | 8:45 | Final Installation of Recovery Section | All Crew | 15 minutes
7 | 44058.0833 | 9:00 | Turn on Rocket verify connections good. | All Crew
8 |  | 9:15 | Roll to Pad | All Crew
9 | 44058.0556 | 9:40 | Photo Opportunity on Pad | All Attendees
10 | 44058.0417 | 10:00 | All Nonessential Personnel return to Spaceport viewing area
11 | 44058.0417 | 10:00 | Start Launch Procedure | All Crew
12 | 44058.0264 | 10:22 | Start Hazardous Ops | All Crew
13 | 44058 | 11:00 | Planned Launch Time | All Eyes
14 | 44057.9972 | 11:04 | Apogee | All Eyes
15 | 44057.9938 | 11:09 | Main Deployment | All Eyes
16 | 44057.9861 | 11:20 | Rocket Lands under Main | All Eyes |  | Nose lands about the same time. Check with Spotters for Location Confirmation.
17 |  |  | Retrieval team to Rocket | 4 to 6 people
18 |  |  | Retrieval team to Nose location | 2 to 4 people
19 |  |  | Pack Trailer and Truck | 2 or 3 people |  | Concurrent Operation with Nose Retrieval
20 |  |  | Post Mission Briefing | John, Neil, Phil, Russ |  | May or may not happen depending on AST Schedule.
21 |  |  | Leave Launch Site | All Crew

## 60 Day Notification Contacts
Email Contacts:
sherman.council@faa.gov;
Henry.Lampazzi@faa.gov;
AST-400@faa.gov;
annette.parks@faa.gov;
jquinn@exosaero.com;
nmilburn@exosaero.com;
smillard@exosaero.com;
peaton@exosaero.com
tlong@exosaero.com;

## Schedule for 15day Notification
Days Before Launch Date | Hours Before Launch Time | Travel | Launch Schedule, ALL TIMES ARE APPROXIMATE | MDT is GMT-6 | 150:00 | Summer, Fall
4 | 3 | 2020-08-11 08:00 | Crane and Rocket Depart to New Mexico - Overnight in Van Horn for crane truck | MST is GMT-7 | 175:00 | Winter, Spring
3 | 23 | 2020-08-11 12:00 | Exos Team pickup and pack Rental Van
3 | 3 | 2020-08-12 08:00 | Exos Team departs for Las Cruces |  |  | Email Contacts:
3 | 1 | 2020-08-12 10:00 | Crane and Rocket trailer continue to site at Spaceport NM |  |  | 15 Day Notification Contacts | sherman.council@faa.gov;
2 | 23 | 2020-08-12 12:00 | Crane and Rocket trailer arrive at Spaceport NM |  |  |  | Henry.Lampazzi@faa.gov;
2 | 19 | 2020-08-12 16:00 | Crane and Rocket trailer team arrives at Las Cruces hotel |  |  |  | AST-400@faa.gov;
2 | 15 | 2020-08-12 20:00 | Exos Team arrives at Las Cruces hotel |  |  |  | annette.parks@faa.gov;
2 |  | 2020-08-13 11:00 | Set Up Day 1
|  | 7:00 | Depart from the Hotel |  |  |  | jquinn@exosaero.com;
|  |  | Unpack Trailer and Truck, Prep Rocket for Combined Systems Test |  |  |  | nmilburn@exosaero.com;
|  | 10:00 | Combined Systems Test |  |  |  | smillard@exosaero.com;
|  | 10:30 | Full Dry Run |  |  |  | peaton@exosaero.com
|  |  | Launch Pad Setup |  |  |  | tlong@exosaero.com;
|  | 12:00 | Break For Lunch
|  |  | Set up recovery system, Set Up Exos Wifi |  |  | 10 day notification contacts. See next tab for data requirement. | 9-asw-zab530@faa.gov;
|  | 16:00 | Get Everything back into the trailer. |  |  |  | 9-AWA-AJR-SPACE.OPS@faa.gov;
|  | 17:00 | Depart Launch Site |  |  |  | spaceops@spaceportamerica.com;
1 |  | 2020-08-14 11:00 | Set Up Day 2 |  |  |  | Craig.Brenden@faa.gov
|  | 7:00 | Depart from Hotel |  |  |  | beth.e.adams@faa.gov;
|  | 8:00 | Unpack trailer, Tightness Check and Reassembly
Start Pressurization on Press Section, Finish Crane Truck Prep for Pad Ops
Payload customers arrive and prepare payloads
|  | 12:00 | Lunch Break
|  | 13:00 | Role Assignment and Training
|  | 17:00 | Mission Readiness Review
0 |  | 2020-08-15 11:00 | Launch Day
|  | 5:00 | Depart from the Hotel
|  | 6:00 | Unpack Trailer
|  | 7:00 | Check Press Section, bump press if needed.
|  | 8:00 | Start Rocket Assembly
|  | 8:30 | Final Installation of Payload Section
|  | 8:45 | Final Installation of Recovery Section
|  | 9:00 | Turn on Rocket verify connections good.
|  | 9:15 | Roll to Pad
|  | 9:40 | Photo Opportunity on Pad
|  | 10:00 | All Nonessential Personnel return to Spaceport viewing area
|  | 10:00 | Start Launch Procedure
|  | 10:22 | Start Hazardous Ops | GMT Summer/fall | GMT Winter/Spring
|  | 44058.4583 | Planned Launch Time | 44064.7083 | 44065.75
|  | 11:04 | Apogee
|  | 11:09 | Main Deployment
|  | 11:20 | Rocket Lands under Main
Retrieval team to Rocket
Retrieval team to Nose location
Pack Trailer and Truck
Post Mission Briefing
|  | End of Day | Leave Launch Site
Formulas:
Travel = 'Master Launch Schedule'!$D2-('Schedule for 15day Notification'!A2+(0.0416*[Hours Before Launch Time]))
Note on B1: Phil Exos: 1 hour = .0416 days

## 10 Day Notification Content
10 Day Notification Requirements |  | Return to Master
Date and Time of Launch | October 26th 2019, 16:00-18:30 GMT (or 10:00-12:30 MDT) Alternate date, October 27th with the same times.
Radius of the Hazard area | 7KM from (32.943694, –106.922361)
Expected Altitude | Expected 90KM, Maximum 105KM
Verify Coordination with White Sands Missile Range | Noted from AST Meeting, verify with Bill Gutman at SPAM
10 Day Notification Email Contacts:
9-asw-zab530@faa.gov;
9-AWA-AJR-SPACE.OPS@faa.gov;
spaceops@spaceportamerica.com;
Craig.Brenden@faa.gov
beth.e.adams@faa.gov;
(c) Notify ZAB Airspace & Procedures Office and ATCSCC Space Operations ten (10) business days in advance of their scheduled launch. If the request is made within ten (10) business days, it will be approved at the discretion of the ZAB Support Manager for Airspace and Procedures. 1. The notification must include:
a. Dates and time of mission, back-up times
b. Radius of Hazard Area
c. Altitude
d. Confirmation that coordination has been accomplished with White Sands Missile Range, if R5107B, R5111A/B/C/D will be affected.

## Final Assembly Checklist
Final Vehicle Assembly Checklist
Item # | Description | Check 1 | Check 2
1 | Fin Can On and Connected
2 | Press Section On and Connected
3 | Main Flight Computer On and Connected
4 | Payload Section On and Connected
5 | Recovery Section On and Connected
6 | Rocket On, All Connections Verified Ready for Flight
Date:

## Recovery Section Checklist
Recovery Section Checklist
Flight Number:____Flight Location:____________________________
Pressurize nose tank to 1100 psi.
Charge nose tracker battery
Ensure yellow pin is installed
Verify GPS Landing Coordinates are programmed into the AGU
Install Main Parachute
Connect the pull cord to the AGU flight switch
Connect the Right and Left control lines to the AGU
Verify the control lines go straight down the spool and not over the top
Verify length of control line on AGU spools
Ensure the recovery system bolts are tight and sealed
Connect the Drogue link to the Kevlar strap leading through the cutters
Ensure cut sensor wire goes through both cutters.
Fan fold and band the strap for flight
Install the screamer between the attach point and the nose cone
Ensure the cutters are connected and capped with the metal cover plate.
Place straps on top of the main parachute container banded in 2 sections.
Place the ballute on top of the straps folded as tight as possible.
Connect the nose wire harness to the bulkhead and secure with a tie wrap
Install the nose on the recovery section using 60 nylon screws
Install the recovery section on the rocket
Completed By __________________ Date ______________

## CPU Pressure Check
CPU Pressure Check |  | Date | ________________
|  |  |  | Completed By | Checked By
1 | Assemble CPU and payload with appropriate seals - Execute CPU to Payload Assembly Checklist
2 | Verify all bolts on pressure sides in place
3 | Turn on CPU using either debug power and RF cables or connected to vehicle
4 | Run ITOS and start CPU press plot
5 | Add 10psi to current CPU pressure using compressed air
6 | Let CPU rest for 2 minutes
7 | Measure initial CPU pressure | Initial pressure
8 | Wait 10 minutes, measure final CPU pressure | Final pressure
9 | Pass < 5psi loss in 10 minutes | Pass/Fail
10 | Proceed to assembling CPU to Press Section

## CPU to Payload Assembly
CPU to Payload Assembly Checklist |  | Date | ______________
|  | Completed By | Checked By
1 | Clean payload o-ring grove
2 | Krytox o-ring and groove
3 | Install o-ring
4 | Connect Main CPU connector
5 | Connect ACS connector
6 | Connect GPS connector and torque
7 | Connect AGU connector and torque
8 | Allign Z- and attach payload to CPU
9 | Secure with 60 10-32 5/16" 100CSK

## CPU to Press Section Assembly
CPU to Press Section Assembly |  | Date | ______________
|  | Completed By | Checked By
1 | Align the computer section with the pressure section in the correct orientation for flight.
2 | Connect the appropriate AN-10 upper ACS gas feed line to the CPU bulkhead connection using an Aluminum seal. Ensure hose orientation lays smoothly and the hose is connected in such a manner as it will not loosen when the CPU section is attached to the pressure section
3 | Connect the sensors, actuators and Lower ACS D connections (3 Cannon Plugs)
4 | Connect the Antennae cables (at least 3) 2 Comms and 1 AGU
5 | Visually inspect to ensure no wires or gas lines will be kinked caught or scraped while sliding the CPU section onto the Pressure section
6 | Secure CPU bulkhead to the pressure section with screws match Z- orientation

## Recovery Glow Plug Test
Recovery Glow Plug Check |  |  |  |  | Date | _____________
[5 empty] | Completed By | Checked By
1 | Disconnect glow plugs, both cutters
Lamp Resistance
2 | Measure impedance between each the two plug leads on each side, should be 2-2.5 ohms |  | Left | Right
3 | Connect leads to glow plugs
Plug impedance
4 | Measure resistance between power wires at the power supply, must be 0.6 - 1.0 ohms |  | Left | Right
5 | Pass / Fail | lamp impedance is not required to pass | Left | Right

## Recovery to Payload Assembly
Recovery to Payload Assembly |  | Date | ________________
|  | Completed By | Checked By
1 | Connect main CPU connector
2 | Connect GPS cable and torque
3 | Connect AGU cable and torque
4 | Align Z- and set recovery into payload section
5 | Secure with 60 10-32 5/16" 100CSK bolts

## Preflight Press Section
SARGE: Preflight pressurization section Field Operations Checklist
The purpose of this checklist is to ensure safe remote pressurization of the high pressure tank used for onboard pressure in the SARGE vehicle.
INITIAL SETUP
1 | Place vehicle pressure section on it's handling cart in a safe location out of the way of work areas and foot traffic
2 | Set Haskel pump transport box adjacent to Press section
3 | Set a FULL Helium 6 pack a few feet from Press section, this is the pressurization supply and control area
4 | Set High Volume High Pressure (HVHP) Helium tanks in same location
5 | Install shade over press section
6 | Unpack the pump box and place the pump on top of the box
7 | Co-locate the Gas powered compressor within easy reach and where the operator is able to easily see the pressure gage on the compressor
8 | Make sure the Haskel pump operating valve is closed
9 | Connect the Compressor air line to the Haskel Pump
10 | Check the oil and start the compressor to make sure it operates, bring it up to full pressure and shut it off
11 | Setup work table, tools and hardware.
12 | Install 6K psi CONCOA regulator on the helium 6 pack.
13 | Connect appropriate length -6AN line between regulator and inlet side of the Haskel Pump
14 | Connect appropriate length -4AN line between the outlet side of the Haskel Pump and the 10K psi calibrated gage. This hose should have a high pressure vent valve to relieve pressure before disconnecting the line.
15 | Zero the 10K gage
16 | Hang the gage in a safe location to make sure it does not fall
COOLING and MONITORING Setup
17 | Place the air conditioning unit on the cart under the pressure section and level with a 3/4 to 1 inch shim
18 | Install the cooling plenum on the bottom end of the pressure section with the fill line passing through the notch on the plenum
19 | Connect Air conditioner to generator power and turn on to begin cooling Receiving tank. Verify that the AC is set to cool and the fan is on high.
20 | Place a fully charged automotive battery next to the Air unit on a wooden board to insulate it from the cart and raise it above any condensation that could come from the Air Conditioner
21 | Install press section monitoring adapter orange case to 2 main cables and 2 thermocouple connections at top of press section
22 | Connect monitoring adapter to the Battery, Blue LED should come on
23 | Connect extended USB cable to laptop located at the pressurization supply and control area.
24 | on Laptop, open press terminal shortcut.
25 | Under the system tab Open settings and select settings appropriate to the press section you are servicing
26 | When the settings window opens click on apply
27 | Connect to the press section GSE adapter using the connect button in the open window on the laptop
28 | Click on F checked for thermocouple data in Fahrenheit and click on filter to get more consistent readings
29 | Numbers close to the travel pressure and a reasonable approximation of temperature should appear. If not, trouble shoot system for leaks, sensor failures, etc. Note Temp and pressure. _________________________
PRESSURIZATION
30 | With the plumbing assembled and not connected to the receiving tank. Secure the high pressure outlet end of the hose to prevent/eliminate hose whip when blowing the line clear
31 | Close all cylinder valves on the helium 6 pack.
32 | Close the CONCOA 6Kpsi regulator
33 | Open the first cylinder to be used on the Helium 6 pack and the main valve and briefly open then close the regulator to blow the entire line clear
34 | Connect the booster pump pressure outlet hose to pressure section of the rocket
35 | Connect thermocouple extensions on the high pressure side of the booster pump to the thermocouple readout unit
36 | Close the High pressure line vent valve
37 | Pressurize the system to 200psi close the regulator and check for leaks with soapy water if available.
38 | Relieve the pressure in the system to avoid rapid overpressure of the rocket high pressure tank if it has lost its pressure charge
39 | Reclose all vents.
40 | Slowly open the receiving tank valve in the pressure section and verify that the pressure showing on the 10K psi gage is at or near the travel pressure allowing for temperature difference.
41 | Set the regulator on the 6 pack to the pressure level of the tank being filled or the max available pressure in the cylinder whichever is LESS.
42 | Carefully recheck all of the plumbing for leaks and correct as needed
43 | With all valves open and fully prepared to fill, open the regulator to 200 psi above tank pressure to begin cascade fill.
44 | Monitor receiving tank temperatures.
45 | When feed pressure falls to within about 100 psi of tank pressure, restart the compressor
46 | When the compressor fills and goes to idle the booster is ready to begin using
47 | Adjust the booster control valve as needed so that the compressor operation is optimized and the pressure/temperature requirements are adhered to.
48 | Monitor tank and pump exit temperatures. Due to sensor latency on the receiving tank, never exceed 125°F as sensed from the highest sensing thermocouple on the tank. If using a heat exchanger, never let the temperature drop below 15°F on the tank. Avoid temperatures in excess of 150°F on the Haskel Pump outlet.
49 | Cascade fill from a single cylinder at a time. Repeating steps 41 through 47 as needed. Ratio of supply tank to receiving tank is dependent upon how fast a fill you desire relative to time available for the tasking, ambient temperature is a factor and tank temperatures shall never be violated.
50 | Switch cylinders when the pressure in the supply cylinder is approximately half that of the pressure in the receiving tank.
51 | When the receiving tank is above 4500 - 4800 psi switch over to one of the HVHP Helium tanks and continue cascade boost until vehicle pressure section is filled to 5200psi operational pressure.
52 | Once operational pressure is reached, stop the flow of gas by turning off the booster pump and let the system rest under pressure for a few minutes.
53 | Close the Helium supply cylinders
54 | Turn off the Compressor
55 | Close vehicle high pressure valve
56 | Check the vehicle pressure section for leaks
57 | Refuel Compressor
58 | Continue to monitor the system through the readout on the laptop
59 | When necessary restart the system and add pressure to compensate for the loss of pressure through cooling of the hardware
60 | Turn air conditioner to "Fan" to keep air flowing through the pressure section while it warms up to prevent moisture from forming.
61 | Open the high pressure line vent valve SLOWLY, hearing protection is required
62 | Allow system to return to ambient temperature and evaluate whether additional pressurization is needed by checking the press terminal readout. If so, pressurize in accordance with the above steps. Upon completion Record press and temp_________
63 | Once the day's operations are complete, press the Disconnect button in the monitoring software and terminate the session.
64 | Disconnect monitoring box from power.
65 | Leave systems in place to the extent that they are secure overnight at the launch prep site.
66 | Protect from weather as needed.
MORNING OF LAUNCH
67 | Reconnect any fittings or electrical connections removed after initial pressurization
68 | Verify Zero on 10K psi gage.
69 | Read press and temp of receiving tank through software. Pressure should reflect the overnight cool down but should not be drastically lower. If so, troubleshoot the system for problems. Record press and temp__________
70 | Barring any problems, start generator and turn on Air conditioner.
71 | Open Highest available pressure cylinder
72 | If pressure is over 4800 fill from unused HVHP cylinder.
73 | Monitor pressure and temperature according to prior instructions.
74 | Once Mission pressure plus 30psi is achieved Closeout pressurization operations
75 | Close all valves and regulators,
76 | Disconnect Fill hardware
77 | Cap fill port on vehicle pressure section.
78 | Using the regulator vent buttons in the monitoring software window, Vent any pressure indicated in the regulation accumulators for 5 minutes prior to disconnecting from monitor.
INSTALLATION ON VEHICLE
79 | Move the pressure section on the cart from the fill point to the vehicle.
80 | Align the pressure section with the vehicle tank section
81 | Connect the Antennae cables (at least 3: H, V, and AGU)
82 | Connect the sensors, actuator connections (Cannon Plugs) and their ground Connectors
83 | Connect the appropriate AN-10 gas feed lines to the ullage connections using Aluminum seals. Ensure hose orientation lays smoothly and connect the lines so they will not loosen when the pressure section is attached to the tank section
84 | Visually inspect to ensure no antenna cables, wires or gas lines will be kinked caught or scraped while sliding the pressure section onto the body of the rocket
85 | Secure press section with 1/4-28 screws to the upper tank bulkhead in the proper orientation. (bolt size for R1-R2. Normally 10-32)
86 | Install "360 fly" cameras (2) into pressure section
87 | Execute CPU to Press Section Checklist when CPU-Payload Press Check is complete

## Engine Bay Preflight Checklist
Engine Bay Preflight Checklist
Tools Needed:
2) 9-16" Wrenches
1) Small Cresent Wrench
1) 7-16" Wrench
1) 3-16" Allen Wrench
1) -10 AN Wrench
1) SMA Torque Wrench (assembly to airframe)
(TS) = verify Torque Seal Paint is intact.
PLUMBING
1 | Fuel pressure transducer hardline both ends (TS)
2 | Fuel overboard dump connection both ends on dump valve inlet side (TS)
3 | Fuel overboard dump hose to valve outlet (PRE-Launch only)
4 | FUEL sanitary From tank adapter to top of valves
5 | FUEL Fill/drain extension on inter-valve plumbing
6 | Flex line from fill/drain extension to igniter solenoid both ends
7 | Fuel Purge connection at bottom of valve set both ends
8 | Fuel Sanitary connection to Main line at bottom of valves
9 | Fuel Sanitary connection from main line to engine
10 | Fuel purge feed from ullage pipe to purge solenoid both ends
11 | ACS Gas feed connection to Ullage pipe
12 | Sanitary clamp connecting LOX downpipe to flex line
13 | LOX purge feed from ullage pipe to purge solenoid both ends
14 | Lox pressure transducer Hardline both ends (TS)
15 | LOX safety return/pressure transducer connection to tank adapter 3 connections to "T" (TS)
16 | LOX overboard dump connection both ends and -4 connection on dump valve inlet side (TS)
17 | LOX overboard dump hose to valve outlet (PRE-Launch only)
18 | Sanitary clamp connecting LOX flex line to top of valve set
19 | LOX fill/drain extension on upper to lower valve plumbing
20 | LOX fill drain extension dash 4 hardline to check valve/igniter line "T" both ends
21 | LOX check valve connection to upper and lower "T" both ends
22 | LOX igniter hose from "T" to igniter solenoid both ends
23 | LOX purge hardline from bottom of valves to purge solenoid both ends
24 | LOX sanitary from bottom of valves to engine feed line
25 | LOX sanitary from feed line to engine
26 | Fuel igniter solenoid hardline to igniter both ends (TS)
27 | LOX igniter solenoid hardline to igniter both ends (TS)
28 | Igniter/chamber pressure transducer hardline both ends
29 | Manual Fuel vent valve dash 10 fittings
30 | Manual LOX vent valve dash 10 fittings
31 | ACS Feed lines on Fin can (8 connections) (TS)
32 | Main ACS connection on Fin Can (1 AN-10 Hose 42" long) (TS)
HARDWARE AND ACTUATORS
33 | Check gimbal beams for weld cracks
34 | Bolts on LOX fill/drain extension (2) (TS)
35 | Bolts on FUEL fill/drain extension (2) (TS)
36 | Nuts on Purge solenoids' bracket (2) (TS)
37 | Gimbal Linear Actuator u-joint bolts to gimbal beams (2)
38 | Gimbal linear actuators lock nuts on threaded shaft to heim joint (4) (TS)
39 | Engine gimbal actuator attach points bolts and lock nuts (2) (TS)
40 | Valve assembly clevis pins and retainer clips (circlips) (2)
41 | Valve actuator clamp rings (2) (TS)
42 | Bolts for Heim joints from thrust cross to gimbal ring (2) (TS)
43 | Gimbal ring bolts (4) (TS)
44 | Lock nuts on engine swing limit bolts (2 on cross 2 on engine) (TS)
45 | Lock nuts on engine load ring heim joints (TS)
46 | Nuts on igniter coil studs
47 | Igniter/chamber pressure transducer secure (Hose clamp to bracket)
48 | Bolts on bottom of igniter solenoids (4) (TS)
ELECTRICAL CONNECTIONS
49 | LOX pressure transducer
50 | Fuel pressure transducer
51 | Chamber pressure transducer
52 | East/West gimbal actuator (Yellow)
53 | East/West gimbal position feedback
54 | North/South gimbal actuator (Green)
55 | North/South gimbal position feedback
56 | Throttle valve Actuator
57 | Throttle Valve position feedback
58 | Master Cutoff (MCO) valve Actuator
59 | MCO Valve position feedback
60 | Igniter actuator
61 | Purge solenoids
62 | Overboard dump valves
63 | Spark plug wire
FIN CAN INSTALLATION
64 | While sliding on the Fin can, Connect FIN CAN ACS line to engine bay ACS AN-10 located behind Manual fuel vent valve
65 | Install Fin can to bulkhead
66 | Install bulkhead screws
67 | Connect fin can Antenna cables to the engine bay Antenna connections inside access port
68 | Connect Fin can Cannon plug to engine bay connection Inside access port
69 | Connect Fin Can Harness ground CPC to engine bay ground CPC
70 | Install access port cover
71 | Connect overboard dump hoses to fin can fittings (2 AN-10 Hoses at the bottom of the fin can near the boat tail)
Sign off 1
sign off 2

## Pad Ops Tools Checklist
Pad Ops Tools Checklist
Pad Tools List
# | Description | Check
1 | Large Sanitary "T" Handle
2 | Vent Valve Handle
3 | Cap T Handles
4 | 2 Crescent Wrenches
5 | Power Supply Box
6 | 2 Inverter Boxes
7 | 2 Extension cords
8 | 12V Heavy duty "Y" Cable
9 | Medium Large Needle Nose Pliars
10 | Wire Cutters
11 | 2 Phillips Screw Drivers
12 | 1 Slot Screw Driver
13 | Fuel Vent Catch Container
14 | Trash Bucket
15

## Rocket Retrieval Tools Checklis
Rocket Retreival Tools Checklist
# | Description | QTY
1 | Yellow Stand
2 | Small Electric Screwdrivers
3 | Manual Screwdrivers
4 | 7/16" Wrenches
5 | 3/4" Socket and ratchet
6 | Dykes
7 | Tank Vent Wrench
8 | Tie Wraps
9 | Containers for screws
10 | Recovery blanket for Main Parachute
11 | Large bin for Main Parachute
12 | Plywood or cardboard to keep dirt out of recovery section
13 | Tripod Lift Device
14 | Lift Strap
15 | Battery for Lift Device

## Personal Equipment Checklist
Personal Equipment and Tools Checklist, Phil
Checklist for: Phil
# | Description | Check
1 | Flight Suit
2 | Hat
3 | Goggles
4 | Extra Dessert Shoes
5 | Spare Rocket Tracking Radio and GPS Equipment
6 | Spare Audio Patch Cords
7 | Recovery System Tool Box
8 | Recovery Laptop
9
10
11
12
13
14
15