Executive Summary: Exos Aerospace Integrated Test Plan

Scorpius Acquisition, BLK3 Flight, and Next-Generation Propulsion Trade Study

Overview

Exos Aerospace is establishing a unified roadmap toward test-only orbital transfer vehicle (OTV) capability. The problem: real reusability needs structures with far fewer parts that still survive repeated cryogenic pressure cycles and launch loads — exactly where composites have historically failed, by microcracking in the cold. The platform combines Exos's reusable suborbital rocket fleet and Integrated Pressurized Structures (IPS) — built on Moon-proven Type-V composite cryogenic tanks from Scorpius Space Launch Company (SSLC), in which Exos owns 18% today — with a next-generation propulsion path (a ~5,800 lbf-class Rotating Detonation Rocket Engine) selected through a structured trade study (NASA MSFC license vs. GTL machined method). Scorpius's TRL-9 tanks flew on Intuitive Machines' Odysseus and Athena lunar landers, and its tank technology has made its first tank sale for an orbital transfer vehicle. Exos is completing its acquisition of Scorpius to bring this composite cryogenic tank technology fully in-house.

As a future, gated orbital path (not funded by the Series A), the program envisions a BLK4 RDRE Test-Only OTV, deployed via rideshare missions on SpaceX Falcon 9 (Transporter), Rocket Lab Electron, or Firefly Alpha. Exos’s suborbital rockets will serve as testbeds for RDRE-powered orbital components—reducing risk, validating subsystems in flight, and bridging to orbital operations without requiring new launch vehicle development.

Strategic Objectives

- Advance Next-Generation Propulsion via a Structured Trade Study: down-select the methane/oxygen RDRE path (NASA MSFC license or GTL machined method) and flight-test it on Exos vehicles toward TRL 8 by 2029 — Exos is the flight-test integrator, not a propulsion provider.

- Leverage Exos Suborbital Fleet: Use Exos’s reusable rockets to flight-test orbital-class propulsion modules, avionics, and recovery systems prior to barge or rideshare deployment.

- Complete the Scorpius Acquisition: bring Scorpius's Type-V composite cryogenic tank technology fully in-house and integrate it into Exos Integrated Pressurized Structures for 20–30% mass reduction and reusable OTV architectures.

- Utilize Texas-Based Infrastructure: Combine Midland, TX ground testing, Gulf of Mexico barge launches, and Exos’s existing suborbital flight capabilities for a comprehensive, iterative development loop.

Phased Implementation Plan

Funding close: Q4 2026 — enables Phase 1 start in January 2027.

Phase 1 (Q1 2027 – Q2 2027): Licensing & Early Integration

- Run the RDRE trade study and down-select — NASA MSFC license (TechPort ID: 116281) vs. GTL machined RDRE method (Exos does not own the GTL technology; both are candidate paths); adapt combustion and injector designs for Exos integration.

- Integrate RDRE with Scorpius Type-V pressurized tankage for the RDREW BLK3 test stage.

- Conduct early hot-fires and composite validation at Midland, TX facilities.

- Prepare Exos suborbital vehicle interfaces for in-flight RDRE component testing.

- Milestones: License executed, PDR complete, first hot-fire by Q2 2027.

Phase 2 (Q3 2027 – Q1 2028): Suborbital RDREW BLK3 Demonstrations

- Conduct 5–7 suborbital flights from The Spaceport Company (TSC) Gulf barge to validate RDRE ignition, throttling, restart, and structural dynamics.

- Integrate RDRE propulsion modules and OTV avionics onto Exos suborbital rockets for partial-duration flight testing and recovery.

- Perform ground-based pre/post-flight analysis in Midland for composite evaluation.

- Milestones: 500+ seconds cumulative in-flight RDRE operation; TRL 7 achieved by end of 2027.

Phase 3 (2028): BLK4 OTV Development and Rideshare Qualification (funded-future — proceeds only with program funding)

- Develop BLK4 test-only OTV (100–500 kg) using RDRE propulsion and Scorpius Type-V tanks integrated by Exos.

- Continue integration testing via Exos suborbital flights for propellant feed, guidance, and recovery systems prior to orbital rideshare readiness.

- Conduct extended-duration RDRE ground burns and vibration testing at Midland.

- Milestones: BLK4 CDR complete; first full-duration 5,800 lbf RDRE test by Q3 2028.

Phase 4 (2028–2031): Orbital Demonstrations & Market Transition (funded-future)

- Execute 3–5 rideshare launches (SpaceX, Rocket Lab, Firefly) to demonstrate RDRE-powered orbital maneuvers—orbit-raising, deorbit, and transfer simulations.

- Use Exos suborbital rockets between orbital missions for iterative design updates and subsystem validation.

- Position test results to support commercial OTV services for NASA, DoD, and commercial clients.

- Milestones: First orbital test Q1 2029; first OTV service contracts by Q3 2029.

Financial Overview

Total Estimated Investment: $65–110 M over 4 years

- NASA RDRE licensing: $1–5 M

- Gulf barge campaign: $5–10 M

- Rideshare missions: $15–25 M (3–5 deployments)

- Ground and suborbital testing (Midland + Exos ops): $10–15 M

- Potential offsets via NASA/DoD programs (SBIR, CLPS, Tipping Point)

- Series A — use of funds: a $10 million Series A to (a) complete the acquisition of Scorpius Space Launch Company (Exos owns 18% today) and bring its composite cryogenic tank technology fully in-house; (b) finish and fly BLK3; (c) advance next-generation propulsion through a structured trade study. BLK4 is not funded by this raise; it remains a future, gated orbital path.

- Company projections: per the Figures of Record and the model of record (v12, consolidated with Scorpius post-acquisition) — Y5 revenue ~$121.6M (conservative Cash Flow case). Management-prepared projections; not audited.

Current Financial Position — FY2025 Actuals (per filed IRS Form 1120):

Revenue $1.49M; EBITDA ~$296K (~20% margin) — first profitable year (pre-tax income $189K).

Total assets $16.1M; ~$6.2M net operating loss carryforward (tax shield on future income).

Target Metrics:

- 90% RDRE efficiency demonstrated

- 80% hardware recovery rate

- <150 kg pressurized structure dry mass

- 3+ successful rideshare tests by 2029

- Commercial OTV-ready platform by 2031

Testing and Trade Study Summary

A comparative analysis of TSC Gulf barge operations and Midland, TX test facilities confirms a hybrid strategy:

- Barge: Optimal for flight safety, recovery operations, and FAA-approved offshore campaigns.

- Midland: Best for ground integration, engine qualification, and suborbital-to-orbital test transitions.

- Exos Suborbital Fleet: Critical bridge for real-flight testing of RDRE components and orbital vehicle systems prior to full orbital deployments.
→ Recommendation: Midland for ground and subsystem integration; Exos suborbital flights for validation; TSC barge for full-system dynamic testing.

Strategic Advantages

- Integrated Flight Test Path: Ground → Suborbital → Barge → Rideshare, minimizing risk and cost per iteration.

- RDRE Advantage: methane/oxygen detonation engine (>350 s Isp potential) via the down-selected path — NASA MSFC license or GTL machined method.

- Reusable Infrastructure: Exos suborbital platforms enable rapid reuse and real-world data collection.

- Cost Efficiency: Rideshare strategy reduces orbital access costs by >60% versus dedicated launch.

- Texas Ecosystem Synergy: Co-located testing, composites manufacturing, and workforce availability.

Next Actions (Q4 2026)

- Complete the acquisition of Scorpius Space Launch Company; run the next-generation propulsion trade study and down-select (NASA MSFC license vs. GTL machined method).

- Modify Exos suborbital vehicles for integrated RDRE subsystem testing.

- Secure TSC barge access and rideshare LOIs (SpaceX, Rocket Lab, Firefly).

- Begin composite structure and avionics PDR integration at Midland.